## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2181-swen-261-08-d backofthebus
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
Sign In: As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | DC; 10/14/2018; Fairly simple to implement. Added signin.ftl, and GetSignInRoute
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | LK; 10/14/2018; Added to signin.ftl
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name, which will be trimmed of any whitespace to avoid similar usernames, and navigate back to the Home page. |  | PR; 10/14/2018; created PostSignInRoute
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  | AH; 10/14/2018
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  | EP; 10/14/2018; Checked list of signed in players and rejects usernames that are within that list
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  | DC; 10/14/2018;
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. |  | EP; 10/14/2018
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | LK; 10/14/2018
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | AH; 10/14/2018
Start Game: As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | EP; 10/14/2018
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | AH; 10/14/2018
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | PR; 10/14/2018
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. |  | LK; 10/14/2018
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | DC; 10/14/2018
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | PR; 10/14/2018
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. |  | DC; 10/14/2018
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | AH; 10/14/2018
Opponent Selection: As a player I want to select an opponent so I can play a game of checkers. | Given that I am signed in when I am at the homepage, then I expect to see a list of players that I can choose from.
Given that I am signed in when I click a players name, then I expect a game to start between me and that player.
Given that I am waiting for a game when another user clicks my name then I will be added to a game with that opponent.
Sign Out: As a player I want to sign out so my game play can end. | Given that I am signed in when I am viewing the homepage or game page, then I expect a way to sign out.
Given that I am signed in when I choose to sign out, then I will be removed from the list of current players.
Given that I am in a game when I sign out, then my opponent will be removed from the game.
Resign: As a player I want to be able to resign at any time so I can save face. | Given that I am in a game when I look at the screen then I expect to see a clickable resign button.
Given that I want to resign when I click the resign button, then I expect to be removed from the game and brought back to the home page.
Given that I am playing in a game when my opponent resigns, then I expect to be brought back to the home screen and told that they have resigned.
Simple Move: As a player, I want to move my piece one space diagonally so that I can advance on my opponent. | Given there is an empty black space in the next row approaching my opponent no more than 1 column away when I drop my single piece, then it will stay there.
Single Jump: As a player, I want to jump my piece over an opponent's piece diagonal to me so that I can capture the piece. | Given that there is an opponent's piece directly diagonal to me and a valid space directly beyond that (towards the same direction), when I try to move a single piece over this valid space then I expect to be able to drop my piece on it.
Given that there is such a valid space as described when I drop my piece on it then I expect the opponent's piece to be removed from the board and added to my collection of their pieces.
Given that my opponent has jumped over my piece when it is an available move then I expect this piece to be removed from my collection of pieces.
Multiple Jump Move: As a player, I want to jump my piece over a series of pieces in diagonal positions so I can capture multiple enemy pieces. | Given that there are multiple, connected single jump moves when it is my turn then I expect to be able to drop my piece on the final valid space.
Given that I have completed a multiple jump move when there is one available, then I expect to have each captured piece involved added to my collection of captured pieces by the end of the turn.
Given that my opponent has completed a multiple jump move when there is one available, then I expect all of my captured pieces to be removed from gameplay by my turn.
Making and Moving Kings: As a player I want to have my pieces converted to kings so that I can achieve a more powerful move. | Given that my piece reaches my opponent's last row when it is a single piece, then my piece becomes a king piece.
Given that my piece is a king piece when I want to move it as defined by simple move or single/multiple jump moves, then it should be able to move backwards or forwards on the board.
Winning by Capture: As a player, I want to win when I capture my opponent's last piece so I can brag to all my friends. | Given I have no pieces left to move when it is my turn, then I lost the game.
Given I have won the game when the game is over then both players are removed from the game and sent back to the home page.
Given I have won the game when the game is over then I am sent a "Win" message.
Given I have won the game when the game is over then my opponent is sent a "Lose" message.
Winning by Stagnation: As a player I want to win when my opponent can no longer move so I can brag to all my friends. | Given that I have no possible valid moves when it is my turn, then I lose the game.
Given that the game has ended when my opponent has run out of valid moves, then a "Win" message is sent to me.
Given that the game has ended when I have run out of valid moves, then a "Lose" message is sent to me.
Given that I have won the game when the game is over then both players are removed from the game and sent back to the home page.
Move Complexity: As a player I want to be obligated to complete the most complex move (multiple jump > single jump > simple move) so that the game progresses. | Given that it's possible for me to make a multiple jump move when I try to make a single jump then it will be an invalid move.
Given that it's possible for me to make a multiple jump when I try to make a simple move then it will be an invalid move.
Given that it's possible for me to make a single jump when I try to make a simple move then it will be an invalid move.
Given that the only possible move is a simple move when I try to make a simple move then it will be valid.
Given that I try to make a simple move when a multiple jump is possible then I will be prompted to look for a multiple jump move.
Given that I try to make a single jump when a multiple jump is possible then I will be prompted to look for a multiple jump move.
Given that I try to make a simple move when a single jump is possible then I will be prompted to look for a single jump move.
List Current Games: As a player I want to see a list of current games from which to choose one to watch. | Given I am on the home screen when I want to spectate a game then I should be shown a list of current games.
Given I see a list of current games when I click a game then I should be directed to a spectator mode screen of the game.
Given a game has finished when I am on the home page then I will no longer see the game in the list.
Show Game: As a developer I want to be able to show the pieces moving around the board the same way as the captured game so the player can watch. | Given the players make a move when I am spectating a game then I should see the change reflected in the board.
Given a player backs up a move when they are attempting to make a valid move, then I won't see it.
Given I am spectating when a player submits a move then I see the change.
Given that I am spectating when the game ends then I am redirected to the home page.
Given that I am spectating when a player resigns then I am redirected to the home page.
Choose Game: As a spectator I want to choose the game I watch so I am not forced to watch the same people over and over. | Given that I am on the home page when I want to spectate then I am shown a list of all the possible games to watch.
Given that I have made a decision when I click a game then I am redirected to the game in specator mode.
Leave Game: As a spectator I want to be able to leave a game I am watching so I am not bored. | Given that I have had enough when I am spectating a game then I can stop watching.
Given that I click leave game when I am spectating then I am redirected to the home page.
Given that I leave the game when I am spectating then I am made available to play checkers.
Given that I am spectating when another player is view the home page, then my name is not clickable to be added to a game on their view.
Anonymity: As a player I want to choose whether or not my identity is known to spectators so I can play games against others without bias. | Given that I am playing a game when a spectator joins then my name is displayed if I allow it.
Given that I am playing a game when a spectator joins then my name appears as Player1 or Player2 if I choose to remain anonymous.
Spectator Count: As a player I want to see how many people are watching me so that I am motivated to play my best. | Given that I am playing a game when a spectator joins then I will see the current number of people watching me.
Given that I am playing a game when another spectator joins then the number of people watching is updated.
Given that I am playing a game when a spectator leaves then the number of people watching is updated.
Capture Game: As a developer I want to record the moves in a game so I can replay them upon request. | Given a move is successfully submitted (do not include backups) when two players are in a game then this move should be stored in a collection of moves.
Show Game: As a developer I want to be able to show the flow of the player's previous game at a pace of their choice so they can analyze their strategy. | Given the view mode is set to replay when the game page is displaying then the appropriate information will be passed into the view model.
Given a player has opted to re-watch their game when it is finished, then they will be able to move forward or backward within the game, one move at a time.
Given a player is in replay mode when they've finished their game, then they are able to quit at any time with the click of a button.
Show Previous Move: As a player I want to choose when to display the previous move that was played so that I can watch the same move over and over. | Given the game mode is set to replay when I am on the game page and not displaying the initial setup then I expect to see a way of moving backwards one move.
Given the game mode is set to replay and the initial setup is being shown when I request to go back a move then I expect an error message.
Given that I am on the replay page when I request to revert a move then I expect the gameboard to revert to the setup before the move was made.
Show Next Move: As a player I want to choose when to show the next move so I can control the flow of the game. | Given the game mode is set to replay when I am on the game page and not displaying the final setup then I expect to see a way of moving forwards one move.
Given the game mode is set to replay and the final board setup is shown when I request to go forward one move then I expect an error message.
Given I am on the replay page when I request to move forward one move then I expect the gameboard to show the next move.